## Function Points
Relation Name | Type | Description | RET | DET | Complexity | FP | Total UFP | Adjustment value | Total AFP | LOC/FP | SLOC
Chat | ILF | Structure for handling messsages in chat | 1 | 3 | Simple | 7 | 52 | 0.83333 | 44 | 15 | 660
Betting | ILF | Structure for betting system and computations | 1 | 6 | Simple | 7
Users | ILF | Structure for user data | 1 | 4 | Simple | 7
RNG | EIF | Structure for generation of random numbers | 1 | 2 | Simple | 5
Operations | Type |  | FTR | DET | Complexity | FP
INS User | EI | Insertion of a new user | 1 | 4 | Simple | 3
INS Mex | EI | Insertion of a new message into chat | 2 | 3 | Simple | 3
INS Bet | EI | Insertion of a bet from the player | 3 | 6 | Simple | 3
UPDT Bet | EI | Update of an existing bet during the game | 3 | 5 | Simple | 3
OUT Sum | EO | Compute final sum of the player bet | 2 | 3 | Simple | 4
OUT Score | EO | Compute final player score | 2 | 2 | Simple | 4
QR Dashboard | EQ | Query dashboard player informations | 1 | 3 | Simple | 3
QR Dices | EQ | Query the dice value obtained at random | 1 | 2 | Simple | 3
Tool used: http://groups.umd.umich.edu/cis/course.des/cis525/js/f00/gamel/introduction.html

## Adjustment Computation
Question | 0 | 1 | 2 | 3 | 4 | 5 | Total
1. Does the system require reliable backup and recovery? |  | X |  |  |  |  | 1
2. Are data communications required? |  |  | X |  |  |  | 2
3. Are there distributed processing functions? |  | X |  |  |  |  | 1
4. Is performance critical? |  | X |  |  |  |  | 1
5. Will the system run in an existing, heavily utilized operational environment? |  | X |  |  |  |  | 1
6. Does the system require on-line data entry? |  |  | X |  |  |  | 2
7. Does the on-line data entry require the input transaction to be built over multiple screens or operations? | X | [5 empty] | 0
8. Are the master file updated on-line? | X | [5 empty] | 0
9. Are the inputs, outputs, files, or inquiries complex? |  | X |  |  |  |  | 1
10. Is the internal processing complex? |  |  | X |  |  |  | 2
11. In the code designed to be reusable? |  |  |  | X |  |  | 3
12. Are conversion and installation included in the design? | X | [5 empty] | 0
13. Is the system designed for multiple installations in different organizations? |  |  | X |  |  |  | 2
14. Is the application designed to facilitate change and ease of use by the user? |  |  |  |  | X |  | 4
Total | [6 empty] | 20

## COCOMO II
MODE | "A" variable | "B" variable | "C" variable | "D" variable | KLOC | EFFORT, (in person-months) | DURATION, (in months) | STAFFING, (recommended)
organic | 6.62 | 0.045139 | 2.5 | 0.026389 | 0.660 | 4.280 | 4.344 | 0.985
Product Attributes |  |  | Project Attributes
Required Reliability | 1.15 (H ) |  | Modern Programming Practices | 1.00 (N )
Database Size | 1.00 (N ) |  | Use of Software Tools | 0.91 (H )
Product Complexity | 1.00 (N ) |  | Required Development Schedule | 1.10 (VH)
Computer Attributes |  |  | New (Values are probably wrong)
Execution Time Constraint | 1.00 (N ) |  | Required reusability | 1.10 (VH)
Main Storage Constraint | 1.00 (N ) |  | Documentation match to life-cycle needs | 1.20 (VH)
Platform Volatility | 1.00 (N ) |  | Personnel continuity | 1.00 (H )
Computer Turnaround Time | 0.87 (L ) |  | Multisite development | 1.15 (XH)
Personnel Attributes
Analyst Capability | 1.46 (VL)
Applications Experience | 1.13 (L )
Programmer Capability | 1.00 (N )
Platform Experience | 1.10 (L )
Programming Language and Tool Experience | 1.00 (N )
Tool usato: https://strs.grc.nasa.gov/repository/forms/cocomo-calculation/