## Product Backlog
Story Number | Story Description | Status | Story points (1-10)
0 | As the product owner I want a distributed system to keep the game available to players | To Do | 5
1 | As a gamer I want a chat to talk with my friends | To Do | 8
2 | As a gamer I need some game mechanics to play the game | To Do | 4
3 | As a gamer I want to bet as much as I want to be more invested in the game | To Do | 2
4 | As a gamer I want to register to keep record of my progresses | To Do | 3
5 | As a gamer I want to login an account to visualize my scoreboard | To Do | 3
6 | As a playing user I want crashes to be avoided to keep playing the game | To Do | 6
Note on A1: Product Owner: Write the name of the story, drag rows according to priorities
Note on B1: Product Owner: Write a detailed description of the story. Be specific about high priority features Make new lines in the same cell with [alt+enter]
Note on C1: Product Owner: Select current status

## Sprint Backlog
Story number | Task Name | Description and details | Check Out | Status | Remaining Effort [hr]
0 | Basic docker infrastructure and sockets | Server structure and socket links |  | Done | 0
0 | Basic communication infrastructure | Code low-level communication APIs: P2P-Link, BEB |  | Done | 0
0 | Perfect failure detector | Basic crash failure system components |  |  | 0
0 | Reliable communication infrastructure | Adding strongest APIs for reliable communication: RB |  | Done | 0
0 | Ordering broadcast messages | Implementing Total Order Broadcast |  | Not To Do | 5
0 | Consensus among servers | Add Consensus protocol to keep data consistency among servers |  | Done | 0
0 | Load balancer functionality | Add a layer between clients and servers to balance the load among the replicas |  | Done | 0
0 | Active replication of servers | Show the remaining effort for each day and a trend to evaluate the possibility of success |  | Done | 0
1 | Chat UI | Create a user friendly chat UI |  | Doing | 2
1 | Integration of communication primitives to chat | Integrate the communication REST APIs to build the chat functionality |  | Done | 0
1 | Add username and avatar to player |  |  | Done | 0
2 | Controls UI | Adding UI for buttons and other controls |  | Done | 0
2 | Random Number Generator | Create a microservice to generate numbers |  | Done | 0
2 | Dice animations | Create an animation for each dice output |  | Done | 0
3 | Bet controls | Adding buttons to let the player bet |  | Doing | 2
3 | Bet rewards calculations | Add the code to compute correct bet output |  | Done | 0
4 | Structure a DB to handle accounts | Replace the simple username system with a real users' DB |  | Done | 0
4 | Create a register account form | This allow new users to register into the system. Their credentials will be saved in the DB |  | Done | 0
5 | Create a login form | This is used by the users to log in and access the game |  | Done | 0
5 | Add custom avatars for players to choose during registration | Add some custom avatars |  | Done | 0
6 | Crash recovery system in Docker | Enable recovery on Docker-compose |  | Done | 0
6 | Recoverable distributed components | Add recover functionality to server components |  | Done | 0
1 | Improve chat and overall UI | Make the UI user friendly and not only functional |  | Done | 0
Note on A1: Feature Name Product Owner: Add the story to the Sprint Backlog Develpment Team: Assign tasks for completion
Note on B1: Development Team: Add a short task name
Note on C1: Development Team: Describe the activity and add comments as needed. Add new lines on the same cell with [alt+enter]
Note on D1: Development Team: Select your name if you are working on it, remove it if you are not working on it anymore so anyone else can pull the activity.
Note on E1: Development Team: Select current status
Note on F1: Development Team: Fill the estimated remaining effort (how many horus of work are left to complete the task)

## Burndown Chart
350
Date | 2023-05-26 | 2023-06-07 | 2023-06-12 | 2023-06-15 | 2023-06-24 | 2023-06-28 | 2023-06-29 | 2023-07-21 | 2023-07-29 | 2023-07-31 | 2023-08-06 | 2023-08-16 | 2023-08-21 | 2023-08-22 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-02 | 2023-09-07 | 2023-09-30 | 2023-10-04
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Real | 350 | 335 | 300 | 282 | 247 | 222 | 187 | 172 | 147 | 120 | 115 | 112 | 82 | 62 | 52 | 38 | 22 | 14 | 6 | 4 | 0
Plan | 350 | 315 | 280 | 245 | 210 | 175 | 140 | 105 | 70 | 35 | 0
Note on A2: Sprint Date At the beginning of the sprint Scrum Master: Assign the dates for the current Sprint
Note on A3: Sprint Day At the beginning of the Sprint Scrum Master: Write the day number
Note on A4: Remaining effort for the respective date. Scrum Master: Fill manually each sprint day with the remaining effort data.
Note on A5: Ideal plan to finish on time At the begining of the sprint Scrum Master: Drag formula as needed to fill the Sprint
Note on A6: Scrum Master: Copy this value to the row Real on today's column. with [ctrl+shit+v]

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Davide Avesani
To Do | Doing | Max Branca
Done | Done | Gabriele Iannola
| OK | Fabrizio Paoluzzi
| Not To Do | Lorenzo Soannini